Appendix A

Table A1. Comprehensive comparison of representative MSRCPSP studies

| Studies | Domain | Worker Type |  | Worker Skills |  | Objective Specifications |  |  | Solution Approaches |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | HT | SS |  | MS | SO | MO | OF |  |
| Li and Womer (2009) | - | ü |  |  | ü | ü |  | TLC | MILP/CP-BDA |
| Heimerl and Kolisch (2010a) | - | ü |  |  | ü | ü |  | TLC | MILP |
| Heimerl and Kolisch (2010b) | - | ü |  |  | ü | ü |  | TC | IPOPT |
| Wongwai and Malaikrisanachalee (2011) | - | - | ü |  | ü | ü |  | Cmax | HA |
| Firat and Hurkens (2012) | TI | - |  |  | ü | ü |  | Cmax | MIP |
| Yannibelli and Amandi (2013) | - | ü |  |  | ü |  | ü | EHR and Cmax | EA |
| Barz and Kolisch (2014) | TI | ü |  |  | ü | ü |  | PC and WC | MDP |
| Montoya et al. (2014) | - | - |  |  | ü | ü |  | Cmax | B&P |
| Attia et al. (2014) | - | ü |  |  | ü | ü |  | TC | GA |
| Correia and Da-Gama (2014) | - | ü |  |  | ü | ü |  | TC | MPM |
| Myszkowski et al. (2015) | - | ü |  |  | ü | ü |  | TC and Cmax | HACO |
| Kia et al. (2016) | - | ü |  |  | ü |  | ü | Cmax, IC and PC | CPLEX |
| Maghsoudlou et al. (2016) | - | ü |  |  | ü |  | ü | TC, Cmax and TQ | MOIWO, NSGA-II and MOPSO |
| Almeida et al. (2016) | - | - |  |  | ü | ü |  | Cmax | PBH |
| Zheng et al. (2017) | - | ü |  |  | ü | ü |  | Cmax | TLBO |
| Javanmard et al. (2017) | IP | ü |  |  | ü |  |  | TC | GAMS solver |
| Maghsoudlou et al. (2017) | - | ü |  |  | ü |  | ü | TC and RRA | MM |
| Chen et al. (2017) | IT | ü |  |  | ü |  | ü | TE, DP and TES | NSGA-II |
| Han et al. (2017) | SI | - | - |  | - | ü |  | OSPS | 3L-PCS |
| Myszkowski et al. (2018) | - | ü |  |  | ü | ü |  | Cmax | DEGR |
| Dai et al. (2018) | - | ü |  |  | ü | ü |  | TC and Cmax | ITS |
| Wang and Zheng (2018) | - | ü |  |  | ü |  | ü | TC and Cmax | MOFOA |
| Zhu et al. (2019) | - | ü |  |  | ü | ü |  | Cmax | DOMVO |
| Najafzad et al. (2019) | ET | ü |  |  | ü |  | ü | TC and Cmax | DMT |
| Zhu et al. (2019) | - |  | ü |  | ü |  | ü | TC and Cmax | NSGA-II |
| Joshi et al. (2019) | - | ü |  |  | ü | ü |  | Cmax | TLBO |
| Felberbauer et al. (2019) | - | ü |  |  | ü | ü |  | EEC | MM and SAA |
| Zabihi et al. (2019) | - | ü |  |  | ü |  | ü | Cmax, TE and CS | TLBO |
| Ahmadpour and Ghezavati (2019) | - | ü |  |  | ü | ü |  | Cmax | CPLEX |
| Tian et al. (2020) | - | ü |  |  | ü |  | ü | TC and Cmax | MOFOA |
| Lin et al. (2020) | - | ü |  |  | ü | ü |  | Cmax | GP-HH |
| Chen et al. (2020) | IT | ü |  |  | ü |  | ü | EL, DC and QDP | ACA |
| Mao et al. (2020) | SI | - | - |  | - | ü |  | OTAC | ICA |
| Li et al. (2020) | - | ü |  |  | ü | ü |  | PE and SD | OS |
| Jeunet and Bou Orm (2020) | - | - | ü |  |  |  | ü | TC, Cmax and QL | MILP |
| Almatroushi et al. (2020) | - | - | ü |  |  | ü |  | TC | OP |
| Zhu et al. (2021) | - | ü |  |  | ü |  | ü | TC and Cmax | MOGP-HH/D |
| Maghsoudlou et al. (2021) | ET | ü |  |  | ü | ü |  | TC | EMA and GA |
| Ghamginzadeh et al. (2021) | - | - |  |  | ü |  | ü | Cmax and TLC | MOICA |
| Snauwaert and Vanhoucke | - | ü | ü |  | ü | ü |  | Cmax | Hybrid GA |
| Barghi and Sikari (2022) | - | ü |  |  | ü | ü |  | Cmax | GA and SA |
| Javanmard et al. (2022) | ET | ü |  |  | ü |  | ü | TC and PPA | GAMS solver |
| Nikaeen and Najafi (2022) | - | ü |  |  | ü | ü |  | Cmax | CP |
| Akbar et al. (2022) | SPS | ü |  |  | ü | ü |  | Cmax | PA |
| Wang et al. (2022) | - | ü |  |  | ü | ü |  | TC | GA-PR |
| Polo-Mejía et al. (2023) | - | ü | ü |  | ü | ü |  | Cmax | GRASP and LNS |
| Ma et al. (2023) | - | ü | ü |  | ü | ü |  | SR | TS |
| Ghasemi et al. (2023) | - | ü |  |  | ü | ü |  | Cmax | TFCP |
| Goudarzi et al. (2023) | - | ü |  |  | ü |  | ü | Cmax and TDRU | KM, FCM and BSOS |
| Han et al. (2024) | PBU | ü |  |  | ü | ü |  | TC | HWOA |
| Chen et al. (2024) | R&D | ü |  |  | ü |  | ü | SKI, TD and RPE | NSGA-II |
| Torba et al. (2024) | HMF | ü |  |  | ü |  | ü | TT and Cmax | MA and SGA |
| Jeunet (2024) | - | ü | ü |  |  | ü |  | TLC | MILP |
| You et al. (2024) | - | ü |  |  | ü | ü |  | TTC | BA |
| Luo et al. (2024) | - | ü |  |  | ü |  | ü | TC and Cmax | MOFOA |
| Goudarzi et al. (2024) | SU | ü |  |  | ü |  | ü | Cmax and TEC | VDO |
| Akbar et al. (2024) | - | ü |  |  | ü | ü |  | Cmax | GPSA |
| Zarei et al. (2024) | RB | ü |  |  | ü |  | ü | Cmax, PC and QPT | IVF-ABS |
| Mozhdehi et al. (2024) | - | ü |  |  | ü | ü |  | Cmax | LSM, TS and MBBO |
| Polancos and Seva (2024) | - | ü |  |  | ü | ü |  | APR | OM and B&C |
| Shahabi-Shahmiri et al. (2024) | SU | ü |  |  | ü |  | ü | Cmax, RC, EC, JO | MILP and AUGMECON2-VIKOR |
| Chen et al. (2025) | SU |  |  |  |  | ü |  | TC | MILP + DRL |
| Snauwaert and Vanhoucke (2025) | - | ü |  |  | ü | ü |  | Cmax | GA and Local Search |
| Mousazadegan et al. (2026) | - | ü |  |  | ü |  | ü | Cmax and TC | SSBI |
| Current study | SI-SSD | ü | ü |  | ü |  | ü | TLC, Cmax and WIC | Scenario-specific NSGA-II configurations |

HM: homogeneous / HT: heterogeneous / SO: single-objective / SS: single-skilled / MS: multi-skilled / MO: multi-objective / OF: objective function / BDA: benders decomposition algorithm / CP: constraint programming / IPOPT: interior point optimizer / HA: heuristic approach / MIP: mixed integer programming / EA: evolutionary algorithm / MDP: Markov decision processes / B&P: branch-and-price / EHR: effectiveness of human resources / WC: waiting cost / MDP: Markov decision processes / TI: telecommunications industry / GA: genetic algorithm / Cmax: makespan / R&D: research and development / TLC: total labor cost / MILP: mixed-integer linear programming / PC: penalty cost / TC: total cost / IC: idle cost / TQ: total quality / PBH: priority-based heuristics / GAMS: general algebraic modeling system / RRA: reworking risks of activities / MM: metaheuristic method / SI: shipbuilding industry / OSPS: optimize shipbuilding project scheduling / IT: information technology / TE: total efficiency / DP: development period / TES: total employee salary / ET: energy tariff / DMT: decision making techniques / EEC: expected external cost / CS: combined salaries / OTAC: optimizing task allocation and collaboration processes / ICA: iterative combination auctions / EL: extent of learning / DC: development cycle / QDP: quality of the developed product / ACA: ant colony algorithm / PE: project effectiveness / SD: skill development / OS: optimization solver / QL: quality losses / OP: optimization package / EMA: electromagnetic like algorithm / PPA: priority-progress alignment / SA: simulated annealing / PA: proposed algorithm / GA-PR: genetic algorithm with priority rules / SR: schedule robustness / TS: tabu search / TDRU: total deviation of resource utilization / KM: K-means / FCM: fuzzy C-means / BSOS: bi-objective symbiosis organisms search / HWOA: hybrid whale optimization algorithm / SKI: skill increment / TD: team diversity / RPE: R&D processes and efficiency / HMF: heavy maintenance factory / TT: total tardiness / MA: memetic algorithm / SGA: simulated genetic algorithm / BA: bat algorithm / TEC: total energy consumption / VDO: vibration damping optimization / RB: railway bridge / QPT: quality of project tasks / IVF-ABS: interval valued-approximate best solution / GPSA: greedy and parallel scheduling algorithm / APR: average project risk / OM: optimization model / B&C: branch-and-cut / LSM: local search method / MBBO: Modified discrete variant of the Biogeography-Based Optimization / SI-SSD: shipyard industry-shipyard steelwork department / WIC: workload imbalance cost / SU: sustainability / RC: resource cost / EC: energy consumption / JO: job opportunities / DRL: deep reinforcement learning / SSBI: skill-sharing block improvement heuristic

References

Ahmadpour S, and Ghezavati V (2019) Modeling and solving multi-skilled resource-constrained project scheduling problem with calendars in fuzzy condition. Journal of Industrial Engineering International 15(1): 179–197. https://doi.org/10.1007/s40092-019-00328-w

Akbar S, Ahmad I, Khan R, Lopes IO and Ullah, R (2022) Multi-skills resource constrained and personality traits based project scheduling. IEEE Access 10: 131419–131429. https://doi.org/10.1109/ACCESS.2022.3229867

Akbar S, Zubair M, Khan R, Ul Akbar U, Ullah R, and Zheng Z (2024) Weighted Multi-Skill Resource Constrained Project Scheduling: A Greedy and Parallel Scheduling Approach. IEEE Access 12: 29824–29836. https://doi.org/10.1109/ACCESS.2024.3350440

Almatroushi H, Hariga M, As’ad R, and Al-Bar AR (2020) The multi resource leveling and materials procurement problem: an integrated approach. Engineering, Construction and Architectural Management 27(9): 2135–2161. https://doi.org/10.1108/ECAM-10-2019-0563

Almeida BF, Correia I, and Saldanha-Da-Gama F (2016) Priority-based heuristics for the multi-skill resource constrained project scheduling problem. Expert Systems with Applications 57: 91–103. https://doi.org/10.1016/j.eswa.2016.03.017

Attia EA, Duquenne P, and Le-Lann JM (2014) Considering skills evolutions in multi-skilled workforce allocation with flexible working hours. International Journal of Production Research 52(15): 4548–4573. https://doi.org/10.1080/00207543.2013.877613

Barghi B, and Sikari SS (2022) Meta-heuristic Solution with Considering Setup Time for Multi-Skilled Project Scheduling Problem. Operations Research Forum 3(1): 1–23. https://doi.org/10.1007/s43069-021-00117-5

Barz C, and Kolisch R (2014) Hierarchical multi-skill resource assignment in the telecommunications industry. Production and Operations Management 23(3): 489–503. https://doi.org/10.1111/poms.12053

Chen L, Zhang J, Chen Z, and Demeulemeester E (2025) Resource-constrained project scheduling problem with hybrid energy and dynamic energy prices. International Journal of Production Research 63(23): 9155–9180. https://doi.org/10.1080/00207543.2025.2535516

Chen R, Gu D, Liang C, and Jiang L (2024) A multi-skilled staff scheduling and team configuration optimisation model for artificial intelligence project portfolio considering competence development and innovation-driven. International Journal of Production Research 62(21): 7763–7792. https://doi.org/10.1080/00207543.2024.2328131

Chen R, Liang C, Gu D and Leung JYT (2017) A multi-objective model for multi-project scheduling and multi-skilled staff assignment for IT product development considering competency evolution. International Journal of Production Research 55(21): 6207–6234. https://doi.org/10.1080/00207543.2017.1326641

Correia I, and Da-Gama F (2014) The impact of fixed and variable costs in a multi-skill project scheduling problem: An empirical study. Computers & Industrial Engineering 72(1): 230–238. https://doi.org/10.1016/j.cie.2014.03.020

Dai H, Cheng W and Guo P (2018) An Improved Tabu Search for Multi-skill Resource-Constrained Project Scheduling Problems Under Step-Deterioration. Arabian Journal for Science and Engineering 43(6): 3279–3290. https://doi.org/10.1007/s13369-017-3047-4

Felberbauer T, Gutjahr WJ and Doerner KF (2019) Stochastic project management: multiple projects with multi-skilled human resources. Journal of Scheduling 22(3): 271–288. https://doi.org/10.1007/s10951-018-0592-y

Firat M and Hurkens CAJ (2012) An improved MIP-based approach for a multi-skill workforce scheduling problem. Journal of Scheduling 15(3): 363–380. https://doi.org/10.1007/s10951-011-0245-x

Ghamginzadeh A, Najafi AA and Khalilzadeh M (2021) Multi-Objective Multi-Skill Resource-Constrained Project Scheduling Problem Under Time Uncertainty. International Journal of Fuzzy Systems 23(2): 518–534. https://doi.org/10.1007/s40815-020-00984-w

Ghasemi M, Chakrabortty RK, Shahabi-Shahmiri R and Mirnezami SA (2023) A chance-constrained programming method with credibility measure for solving the multi-skill multi-mode resource-constrained project scheduling problem. International Journal of Construction Management 24(10): 1090–1106.  https://doi.org/10.1080/15623599.2023.2252255

Goudarzi E, Esmaeeli H, Parsa K and Asadzadeh S (2023) Proposing new clustering-based algorithms for the multi-skilled resource-constrained multi-project scheduling problem with resource leveling adjustments. Kybernetes 54(2): 1049-1081. https://doi.org/10.1108/K-06-2023-1044

Goudarzi E, Esmaeeli H, Parsa K and Asadzadeh S (2024) Energy-efficient resource-constrained multi-project scheduling problem with generalized precedence relations and multi-skilled resources. Journal of Supercomputing 80(10) 13837–13872. https://doi.org/10.1007/s11227-024-05933-0

Han D, Yang B, Li J, Sun M, Zhou Q and Wang J (2017) A three-layer parallel computing system for shipbuilding project scheduling optimization. Advances in Mechanical Engineering 9(10): 1-17. https://doi.org/10.1177/1687814017723297

Han J, Chen C, Tiong R K, and Wu K (2024) Smart multi-project scheduling and multi-skilled workforce assignment for prefabricated bathroom unit production. Automation in Construction 166: 105626. https://doi.org/10.1016/j.autcon.2024.105626

Heimerl C and Kolisch R (2010a) Scheduling and staffing multiple projects with a multi-skilled workforce. OR Spectrum 32(2): 343–368. https://doi.org/10.1007/s00291-009-0169-4

Heimerl C and Kolisch R (2010b) Work assignment to and qualification of multi-skilled human resources under knowledge depreciation and company skill level targets. International Journal of Production Research 48(13): 3759–3781. https://doi.org/10.1080/00207540902852785

Javanmard, S., Afshar-Nadjafi, B., & Akhavan Niaki, S. T. (2017). Preemptive multi-skilled resource investment project scheduling problem: Mathematical modelling and solution approaches. Computers & Chemical Engineering, 96, 55–68. https://doi.org/10.1016/j.compchemeng.2016.11.001

Javanmard S, Afshar-Nadjafi B and Taghi Akhavan Niaki S (2022) A bi-objective model for scheduling of multiple projects under multi-skilled workforce for distributed load energy usage. Operational Research 22(3): 2245–2280. https://doi.org/10.1007/s12351-021-00633-6

Jeunet J (2024) Project acceleration using temporary workers with heterogeneous efficiency: optimal and best recruitment policies. International Journal of Production Research 62(17): 6102–6119. https://doi.org/10.1080/00207543.2024.2308691

Jeunet J and Bou Orm M (2020) Optimizing temporary work and overtime in the Time Cost Quality Trade-off Problem. European Journal of Operational Research 284(2): 743–761. https://doi.org/10.1016/j.ejor.2020.01.013

Joshi D, Mittal ML, Sharma MK and Kumar M (2019) An effective teaching-learning-based optimization algorithm for the multi-skill resource-constrained project scheduling problem. Journal of Modelling in Management 14(4): 1064–1087. https://doi.org/10.1108/JM2-07-2018-0108

Kia R, Shahnazari-Shahrezaei P and Zabihi S (2016) Solving a multi-objective mathematical model for a Multi-Skilled Project Scheduling Problem by CPLEX solver. In: IEEE International Conference on Industrial Engineering and Engineering Management, December 4-7, Bali, Indonesia, pp. 1220–1224. https://doi.org/10.1109/IEEM.2016.7798072

Li H and Womer K (2009) Scheduling projects with multi-skilled personnel by a hybrid MILP/CP benders decomposition algorithm. Journal of Scheduling 12(3): 281–298. https://doi.org/10.1007/s10951-008-0079-3

Lin J, Zhu L and Gao K (2020) A genetic programming hyper-heuristic approach for the multi-skill resource constrained project scheduling problem. Expert Systems with Applications 140: 112915. https://doi.org/10.1016/j.eswa.2019.112915

Luo X, Guo S, Du B, Luo X and Guo J (2024) Multi-Objective Multi-Skill Resource-Constrained Project Scheduling Considering Flexible Resource Profiles. Applied Sciences 14(5): 1921. https://doi.org/10.3390/app140519214051921

Ma Y, He Z, Wang N and Demeulemeester E (2023) Tabu search for proactive project scheduling problem with flexible resources. Computers & Operations Research 153: 106185. https://doi.org/10.1016/j.cor.2023.106185

Maghsoudlou H, Afshar-Nadjafi B and Akhavan Niaki ST (2017) Multi-skilled project scheduling with level-dependent rework risk; three multi-objective mechanisms based on cuckoo search. Applied Soft Computing 54: 46–61. https://doi.org/10.1016/j.asoc.2017.01.024

Maghsoudlou H, Afshar-Nadjafi B and Niaki STA (2016) A multi-objective invasive weeds optimization algorithm for solving multi-skill multi-mode resource constrained project scheduling problem. Computers & Chemical Engineering 88: 157–169. https://doi.org/10.1016/j.compchemeng.2016.02.018

Maghsoudlou H, Afshar-Nadjafi B and Niaki STA (2021) A framework for preemptive multi-skilled project scheduling problem with time-of-use energy tariffs. Energy Systems 12(2): 431–458. https://doi.org/10.1007/s12667-019-00374-8

Montoya C, Bellenguez-Morineau O, Pinson E and Rivreau D (2014) Branch-and-price approach for the multi-skill project scheduling problem. Optimization Letters 8(5): 1721–1734. https://doi.org/10.1007/s11590-013-0692-8

Mousazadegan H, Fatemi Ghomi SMT and Afrazeh A (2026) A novel approach to improve workforce skills in the multi-skilled project scheduling problem using the apprenticeship method. Computers & Industrial Engineering 211: 111651. https://doi.org/10.1016/j.cie.2025.111651

Mozhdehi S, Baradaran V and Hosseinian AH (2024) Multi-skilled resource-constrained multi-project scheduling problem with dexterity improvement of workforce. Automation in Construction 162: 105360. https://doi.org/10.1016/j.autcon.2024.105360

Myszkowski PB, Olech ŁP, Laszczyk M and Skowroński ME (2018) Hybrid Differential Evolution and Greedy Algorithm (DEGR) for solving Multi-Skill Resource-Constrained Project Scheduling Problem. Applied Soft Computing 62: 1–14. https://doi.org/10.1016/j.asoc.2017.10.014

Myszkowski PB, Skowroński ME, Olech ŁP and Oślizło K (2015) Hybrid ant colony optimization in solving multi-skill resource-constrained project scheduling problem. Soft Computing 19(12): 3599–3619. https://doi.org/10.1007/s00500-014-1455-x

Najafzad H, Davari-Ardakani H and Nemati-Lafmejani R (2019) Multi-skill project scheduling problem under time-of-use electricity tariffs and shift differential payments. Energy 168: 619–636. https://doi.org/10.1016/j.energy.2018.11.070

Nikaeen R and Najafi AA (2022) A Constraint Programming Approach to Solve Multi-skill Resource-constrained Project Scheduling Problem with Calendars. International Journal of Engineering 35(8): 1579–1587. https://doi.org/10.5829/ije.2022.35.08b.14

Polancos RV and Seva, RR (2024) A Risk Minimization Model for a Multi-Skilled, Multi-Mode Resource-Constrained Project Scheduling Problem with Discrete Time-Cost-Quality-Risk Trade-Off. Engineering Management Journal 36(3): 272–288. https://doi.org/10.1080/10429247.2023.2264161

Polo-Mejía O, Artigues C, Lopez P, Mönch L and Basini V (2023) Heuristic and metaheuristic methods for the multi-skill project scheduling problem with partial preemption. International Transactions in Operational Research 30(2): 858–891. https://doi.org/10.1111/itor.13063

Shahabi-Shahmiri R, Tavakkoli-Moghaddam R, Dolgui A, Mirnezami SA, Ghasemi M and Ahmadi M (2024) Preemptive and non-preemptive multi-skill multi-mode resource-constrained project scheduling problems considering sustainability and energy consumption: A comprehensive mathematical model. Journal of Environmental Management 367: 121986. https://doi.org/10.1016/j.jenvman.2024.121986

Snauwaert J and Vanhoucke M (2021) A new algorithm for resource-constrained project scheduling with breadth and depth of skills. European Journal of Operational Research 292(1): 43–59. https://doi.org/10.1016/j.ejor.2020.10.032

Snauwaert J and Vanhoucke M (2025) A solution framework for multi-skilled project scheduling problems with hierarchical skills. Journal of Scheduling 28(3): 289–310. https://doi.org/10.1007/s10951-025-00836-1

Tian Y, Xiong T, Liu Z, Deng P and Wan L (2020) Novel Feedback-based Operators in Solving Multi-skill Resource-Constrained Project Scheduling Problem. In: Proceedings of the 32nd Chinese Control and Decision Conference, August 22–24, 2018, Hefei, China, pp. 296-301. Available at: https://doi.org/10.1109/CCDC49329.2020.9164711

Torba R, Dauzère-Pérès S, Yugma C, Gallais C and Pouzet J (2024) Solving a real-life multi-skill resource-constrained multi-project scheduling problem. Annals of Operations Research 338(1): 69–114. https://doi.org/10.1007/s10479-023-05784-7

Wang L and Zheng X. long (2018) A knowledge-guided multi-objective fruit fly optimization algorithm for the multi-skill resource constrained project scheduling problem. Swarm and Evolutionary Computation 38: 54–63. https://doi.org/10.1016/j.swevo.2017.06.001

Wang M, Liu G and Lin X (2022) Dynamic Optimization of the Multi-Skilled Resource-Constrained Project Scheduling Problem with Uncertainty in Resource Availability. Mathematics 10(17): 3070. https://doi.org/10.3390/math10173070

Wongwai N and Malaikrisanachalee S (2011) Augmented heuristic algorithm for multi-skilled resource scheduling. Automation in Construction 20(4): 429–445. https://doi.org/10.1016/j.autcon.2010.11.012

Yannibelli V and Amandi A (2013) Project scheduling: A multi-objective evolutionary algorithm that optimizes the effectiveness of human resources and the project makespan. Engineering Optimization 45(1): 45–65. https://doi.org/10.1080/0305215X.2012.658782

You W, Xu Z and Zhao S (2024) A Two-Layer Approach for the Decentralized Multi-Project Scheduling Problem Sharing Multi-Skilled Staff. IEEE Access 12: 29204–29221. https://doi.org/10.1109/ACCESS.2024.3369177

Zabihi S, Rashidi Kahag M, Maghsoudlou H and Afshar-Nadjafi B (2019) Multi-objective teaching-learning-based meta-heuristic algorithms to solve multi-skilled project scheduling problem. Computers & Industrial Engineering 136: 195–211. https://doi.org/10.1016/j.cie.2019.07.032

Zarei F, Arashpour M, Mirnezami SA, Shahabi-Shahamiri R and Ghasemi M (2024) Multi-skill resource-constrained project scheduling problem considering overlapping: fuzzy multi-objective programming approach to a case study. International Journal of Construction Management 24(8): 820–833. https://doi.org/10.1080/15623599.2023.2260696

Zheng H yu, Wang L and Zheng X long (2017) Teaching–learning-based optimization algorithm for multi-skill resource constrained project scheduling problem. Soft Computing 21(6): 1537–1548. https://doi.org/10.1007/s00500-015-1866-3

Zhu C, Xue Y, He Z, Bao Z, Zhang Z and Hu K (2019) A Multi-objective Model for Multi-skill Project Scheduling Problem considering Perform Efficiency. In: Proceedings of the International Conference on Industrial Engineering and Systems Management, September 25-27, 2019, Shanghai, China, Available at: https://doi.org/10.1109/IESM45758.2019.8948152

Zhu L, Lin J, Li YY and Wang ZJ (2021) A decomposition-based multi-objective genetic programming hyper-heuristic approach for the multi-skill resource constrained project scheduling problem. Knowledge-Based Systems 225: 107099. https://doi.org/10.1016/j.knosys.2021.107099

Zhu L, Lin J and Wang ZJ (2019) A discrete oppositional multi-verse optimization algorithm for multi-skill resource constrained project scheduling problem. Applied Soft Computing 85: 105805. https://doi.org/10.1016/j.asoc.2019.105805

Appendix B. Post-optimization analysis of WIP cost

Following the optimization process, the total operational cost is evaluated by combining the optimized labor cost with the scenario-specific WIP cost, which is calculated separately as a post-optimization accounting term. The corresponding percentage contributions of labor cost and WIP cost under all workforce configurations are presented in Appendix (Figures. B1 and B2).

As shown in Figures B1 and B2, the relative contribution of WIP cost increases as the number of workstations (|I|) increases. Since the experiments are organized according to three workstation levels (|I| = 12, 16, and 20), the WIP cost contribution gradually increases across Experiments 1–9, 10–18, and 19–27, respectively. This trend is expected because the WIP cost is determined by workstation-related precedence characteristics and therefore becomes more pronounced as the production system grows.

A comparison of the workforce configurations further reveals that the single-skilled workforce configurations (A1 and A2) exhibit consistently higher WIP cost contributions than the corresponding multi-skilled workforce configurations (A3 and A4). Although single-skilled workforce configurations generally require lower direct labor costs, the higher relative WIP cost indicates that they are more susceptible to material accumulation during production. In contrast, the flexibility provided by multi-skilled workers reduces the relative contribution of WIP cost to the total operational cost, indicating more efficient material flow and resource utilization within the SSD.

Finally, changing the number of panel-line workstations (|L| = 5, 7, and 9) has only a marginal influence on the relative contribution of WIP cost. The percentages remain relatively stable across different panel-line levels, suggesting that WIP cost is primarily affected by the overall workstation structure and precedence relationships rather than by the number of panel-line workstations.

Figure B1. Percentage contributions of labor cost and WIP cost to the post-optimization total operational cost for A1 and A2 under different panel-line workstation levels (|L| = 5, 7, and 9).

Figure B2. Percentage contributions of labor cost and WIP cost to the post-optimization total operational cost for A3 and A4 under different panel-line workstation levels (|L| = 5, 7, and 9).

Appendix C. Additional details of the mathematical model

Equations (1)–(3) define the three objective functions considered in the proposed model. Eq. (1) minimizes the total labor cost. Labor cost is associated with assigning workers to workstations according to their skill levels and proficiency scores. Eq. (2) minimizes the overall project completion time, denoted by the makespan Cmax. This objective ensures that the total duration required to complete all workstation tasks is reduced as much as possible. The makespan Cmax represents the maximum completion time among all workstation tasks and is determined through the constraint Cmax≥fi for all i∈I.

Eq. (3) minimizes workforce workload imbalance by reducing the difference between the maximum and minimum workloads assigned to workers. This objective promotes a more balanced distribution of tasks among workers. In this context, the workload of each worker WLr is first calculated based on the processing times of the tasks assigned to that worker. Subsequently, the auxiliary variables MXWI and MNWI represent the maximum and minimum workload through linear constraints. The workload imbalance is then measured as the difference between these two values.

Eq. (4) defines the total operational cost used exclusively for post-optimization cost evaluation. After the optimization process has been completed, the optimized labor cost is combined with the configuration-specific WIP cost associated with material accumulation at workstations. In the SSD environment, workstations with a higher number of predecessor tasks tend to experience greater material accumulation. This may result in additional efforts to locate materials within the accumulated inventory, increased transportation requirements, and potential material deterioration caused by compaction or deformation. The WIP cost is therefore calculated separately to represent these operational consequences and is added to the optimized labor cost only after optimization. The WIP cost at workstation i is parameterized by Φiχ(αi μi), where μi denotes the number of predecessor tasks and αi indicates whether workstation i has at least one predecessor.

Here, Φiχ denotes the WIP cost coefficient under workforce configuration, where χ∈{single,multi}. The second term represents a scenario-dependent WIP cost component. Since Φiχ, αi and μi are exogenous parameters, the WIP cost remains constant across candidate solutions within a given workforce configuration. It is therefore calculated separately and used only to evaluate total operational cost after optimization.

Eqs. (5)–(8) define the precedence and timing relationships among workstation tasks. Eq. (5) enforces the precedence relationships by ensuring that a successor task cannot start before the completion of its predecessor.

Eq. (6) determines the completion time of the task at each workstation as the sum of its start time and effective processing time. The effective processing time, denoted by τi, is an assignment-dependent derived variable rather than a fixed input parameter. During the evaluation of each candidate solution, the decoding procedure first identifies the workers assigned to each skill required at workstation i. It then calculates τi based on the nominal processing times of the required skills and the proficiency scores of the assigned workers. Therefore, different worker–skill assignments may produce different effective processing times for the same workstation. Once τi has been calculated for a particular candidate solution, its completion time is obtained from Eq. (6). More specifically, the effective processing time is calculated as τi=round(k∈Sτikr∈Wψr).

For example, suppose workstation i=6 requires four skills (skill 1, skill 2, skill 3 and skill 5), whose nominal processing times are τ61=132, τ62=85, τ63=214, and τ65=88, respectively. Assume that worker 16 ​ and worker 26 ​ are assigned to skill 1, worker 22​ and worker 29 ​to skill 2, worker 6 to skill 3, and worker 7 to skill 5. Their corresponding proficiency levels are ψ16=0.83, ψ26=0.81, ψ22=0.75, ψ29=1.25, ψ6=0.76, and ψ7=1.21. Accordingly, the effective processing time of workstation 6 is calculated as τ6=132(0.83×0.81)+85(0.75×1.25)+214(0.76)+88(1.21)=438.

This multiplicative relationship is adopted as a modeling assumption to represent the combined effect of the workers assigned to the same skill and their proficiency scores. Thus, τi is recalculated for every candidate solution within the NSGA-II decoding procedure and is not held constant throughout the optimization process. After τi has been calculated, the decoder schedules the task without interruption over the interval [si, fi), where fi=si+τi. Therefore, task non-preemption is enforced during schedule generation.

Eq. (7) defines the project makespan Cmax by ensuring that it is greater than or equal to the completion time of every workstation task. Eq. (8) ensures that the completion time of each workstation task does not exceed the predefined project deadline D. Eqs. (9)–(11) establish the workload imbalance structure used in the third objective function. Specifically, Eq. (9) calculates the total workload assigned to each worker based on the processing times of the tasks performed. Eqs. (10) and (11) define the auxiliary variables representing the maximum and minimum workloads among workers, which are later used to measure workload imbalance. Eqs. (12)–(14) ensure the feasibility and correctness of skill assignments. Eq. (12) guarantees that a worker can only be assigned to perform a skill if the worker possesses the required capability. Eq. (13) satisfies the skill requirements at each workstation by assigning the required number of workers to each skill type. Eq. (14) restricts workers to performing at most one skill role at a workstation.

Eqs. (15) and (16) concern worker-time allocation and resource availability. Eq. (15) ensures that the total number of periods allocated to worker r at workstation i equals the effective processing time τi when that worker is assigned to one of the skills required by the task. Eq. (16) prevents a worker from being allocated to more than one workstation task in the same period. Eq. (15) specifies the total allocation time but does not, by itself, impose consecutiveness across these periods. Consecutive allocation is enforced by the NSGA-II decoding procedure. Specifically, after the workers required for workstation i have been selected and τi has been calculated, the decoder identifies the earliest starting time at which all selected workers are simultaneously available for the entire interval of length τi. The task is then scheduled without interruption over [si, fi), and the same workers remain assigned throughout this interval. Consequently, neither task pre-emption nor worker substitution is permitted after task execution has started.

Eqs. (17) and (18) determine the start time of each workstation task through the time-indexed start variable zi,t. Eq. (17) ensures that each task starts exactly once within the planning horizon, while Eq. (18) derives si from the selected starting period. The resulting start time is used by the decoding procedure together with τi to establish the uninterrupted execution interval [si, fi). Eq. (19) guarantees that each workstation task requires at least one skill type. Finally, Eqs. (20) and (21) define the domain restrictions of the decision and continuous variables used in the model.

Appendix D. Listings for pseudo codes

| Listing 1: Workforce configuration -based encoding and worker assignment procedure |  |
| --- | --- |
| 1 | inputs: Number of tasks (¦I¦), worker-skill matrix, task-skill requirements, workforce configuration (A1, A2, A3 or A4) |
| 2 | output: encoded task sequence, worker assignment matrix |
| 3 | begin |
| 4 | Generate a random permutation of tasks |
| 5 | Initialize the worker assignment matrix |
| 6 | Initialize the available worker pool |
| 7 | for each task in the encoded sequence do |
| 8 | Identify the skill types required by the task |
| 9 | for each required skill do |
| 10 | Determine the number of workers required for that skill |
| 11 | Select the eligible worker set according to the configuration: |
| 12 | If configuration = A1: |
| 13 | choose single-skilled workers under specialization-based assignment |
| 14 | else if configuration = A2: |
| 15 | choose single-skilled workers under flexibility-based assignment |
| 16 | else if configuration = A3: |
| 17 | choose multi-skilled workers under specialization-based assignment |
| 18 | else if configuration = A4: |
| 19 | choose multi-skilled workers under flexibility-based assignment |
| 20 | Randomly assign the required number of workers from the eligible set |
| 21 | Remove assigned workers from the current available pool when reuse is not allowed |
| 22 | end for |
| 23 | Store worker assignments for the task |
| 24 | end for |
| 25 | Decode the chromosome using the precedence-preserving decoding procedure |
| 26 | Return the encoded task sequence and worker assignment matrix |
| 27 | end |

| Listing 2: SSS-based decoding and fitness evaluation procedure |  |
| --- | --- |
| 1 | inputs: workforce size (¦W¦), number of workstations (¦I¦), number of skills (¦S¦), population size (ps), task times for each skill, precedence relations among workstations, skill assignment sets for workers, total number of skills required per workstation, worker skill matrix, per-unit cost of worker r (λrχ), work-in-progress cost (Φiχ), configuration type (A1, A2, A3 or A4), αi, number of predecessor (μi), population of task sequences, population of worker assignments |
| 2 | output: objective values of labor cost, makespan, and workload imbalance |
| 3 | begin |
| 4 | Determine workstation task processing times for all individuals according to configuration type: |
| 5 | if configuration type = A1 or A2 then |
| 6 | Compute processing times using single-skilled worker proficiency data |
| 7 | elseif configuration type = A3 or A4 then |
| 8 | Compute processing times using multi-skilled worker proficiency data |
| 9 | end if |
| 10 | for each individual a = 1 to ps do |
| 11 | Gather all workers assigned in chromosome a across all workstations |
| 12 | Compute labor cost: |
| 13 | total labor cost ← 0 |
| 14 | for each assign worker do |
| 15 | Add the corresponding worker cost to labor cost |
| 16 | end for |
| 17 | Initialize si and fi vectors for all tasks at workstation as zero |
| 18 | i ← task sequence (a,1) |
| 19 | si ← 0 |
| 20 | fi ← si + τi |
| 21 | for each chromosome position b = 2 to ¦I¦ do |
| 22 | i ← population of task sequences (a, b) |
| 23 | Previously scheduled workstations ← population of task sequences (a, 1:i-1) |
| 24 | Identify predecessor-related conflicts: |
| 25 | for each previously scheduled workstation task do |
| 26 | if it is a predecessor of current workstation then |
| 27 | mark predecessor conflict = 1 |
| 28 | else |
| 29 | mark predecessor conflict = 0 |
| 30 | end if |
| 31 | end for |
| 32 | Identify worker-sharing conflicts: |
| 33 | Compare workers assigned to current workstation with workers assigned to each previously scheduled workstation task |
| 34 | if at least one common worker exist then |
| 35 | mark predecessor conflict = 1 |
| 36 | else |
| 37 | mark predecessor conflict = 0 |
| 38 | end if |
| 39 | Determine earliest feasible start time si: |
| 40 | Case 1: |
| 41 | if current workstation has no predecessor conflict and no worker-sharing conflict then |
| 42 | si ← 0 |
| 43 | Case 2: |
| 44 | if current workstation has predecessor conflict only then |
| 45 | si ← maximum fi among its predecessor workstations |
| 46 | Case 3: |
| 47 | if current workstation has worker-sharing conflict only then |
| 48 | si ← earliest time that does not overlap with workstation sharing common workers |
| 49 | Case 4: |
| 50 | if current workstation has both predecessor conflict and worker-sharing conflict then |
| 51 | si ← maximum of: |
| 52 | (i) maximum fi among predecessor activities |
| 53 | (ii) earliest non-overlapping time with respect to activities sharing common workers |
| 54 | Compute finish time: |
| 55 | fi ← si + processing times (current workstation, a) |
| 56 | end for |
| 57 | Compute makespan: |
| 58 | makespan ← maximum fi over all workstations |
| 59 | Initialize worker workloads as zero |
| 60 | for each chromosome position b = 1 to ¦I¦ do |
| 61 | workstation ← population of task sequences (a, b) |
| 62 | assigned workers ← population of worker assignments (a, b) |
| 63 | for each worker assigned to this workstation do |
| 64 | Add processing times (workstation, a) to that worker's accumulated workload |
| 65 | end for |
| 66 | end for |
| 67 | Compute workload imbalance: |
| 68 | maximum workload ← maximum worker workload |
| 69 | minimum workload ← minimum worker workload |
| 70 | Workload imbalance ← maximum workload - minimum workload |
| 71 | objective values (a, 1) ← total labor cost |
| 72 | objective values (a, 2) ← makespan |
| 73 | objective values (a, 3) ← workload imbalance |
| 74 | end for |
| 75 | Return objective values and processing times |
| 76 | end |

| Listing 3: Initialization process for NSGA-II-based algorithms |  |
| --- | --- |
| 1 | inputs: ¦I¦ (workstations), ps (population size), precedence constraints among workstations, worker skill sets, aggregate skill counts for workstations, worker–skill incidence matrix |
| 2 | output: starting population |
| 3 | begin |
| 4 | while ps is not obtained do |
| 5 | Generate an encoding using a randomized strategy |
| 6 | Allocate workers to workstations according to skill demands |
| 7 | end while |
| 8 | return the generated initial population |
| 9 | end |

| Listing 4: Binary tournament selection with crowding distance (NSGA-II) |  |
| --- | --- |
| 1 | inputs: current population, objective values, ps (population size) |
| 2 | output: intermediate population |
| 3 | begin |
| 4 | Perform non-dominated sorting on the current population |
| 5 | Compute crowding distance values for all solutions within each front |
| 6 | Initialize the intermediate population as empty |
| 7 | while size of intermediate population < ps do |
| 8 | Randomly select two candidate solutions from the current population |
| 9 | Compare their non-dominated ranks |
| 10 | Select the solution with the lower rank |
| 11 | If both candidates have the same rank, select the one with the larger crowding distance |
| 12 | If both rank and crowding distance are equal, choose one solution randomly |
| 13 | Add the selected solution to the intermediate population |
| 14 | end while |
| 15 | Return the intermediate population |
| 16 | end |

| Listing 5: One-point crossover with precedence-preserving repair |  |
| --- | --- |
| 1 | inputs: ps (population size), ¦I¦ (workstations), set of the chromosome pairs, precedence and successor relations matrix, probability of crossover (pc) |
| 2 | output: the new solutions |
| 3 | begin |
| 4 | while offspring count < ps do |
| 5 | Select parent-A and parent-B |
| 6 | if rand () < pc then |
| 7 | Randomly select a cut point q, 1 ≤ q < ¦I¦ |
| 8 | Create offspring-A by combining: |
| 9 | first q genes of parent-A |
| 10 | last ¦I¦-q genes of parent-B |
| 11 | Create offspring-B by combining: |
| 12 | first q genes of parent-B |
| 13 | last ¦¦I¦-q genes of parent-A |
| 14 | For each offspring do |
| 15 | Identify duplicated workstation genes in the second segment |
| 16 | Remove duplicated genes from the offspring |
| 17 | Identify missing workstation genes |
| 18 | For each missing workstation gene g do |
| 19 | Determine the position of the latest predecessor of g already present in the offspring |
| 20 | Determine the position of the earliest successor of g already present in the offspring |
| 21 | if no predecessor and no successor of g is present then |
| 22 | Insert g at the beginning of the offspring |
| 23 | else if no predecessor is present and at least one successor is present then |
| 24 | Insert g before the earliest successor |
| 25 | else if at least one predecessor is present and no successor is present then |
| 26 | Insert g after the latest predecessor |
| 27 | else |
| 28 | Insert g between the latest predecessor and the earliest successor |
| 29 | end if |
| 30 | if no feasible insertion position exists then |
| 31 | Restore the offspring using the corresponding parent chromosome |
| 32 | end if |
| 33 | end for |
| 34 | Reassign worker genes according to the repaired workstation sequence |
| 35 | Validate the offspring for duplicate workstation genes and precedence feasibility |
| 36 | end for |
| 37 | else |
| 38 | Copy parent-A and parent-B directly to the offspring population |
| 39 | end if |
| 40 | Add offspring-A and offspring-B to the offspring population |
| 41 | end while |
| 42 | end |

| Listing 6: Mutation process: pseudo-code representation |  |
| --- | --- |
| 1 | inputs: probability of mutation (pm), population size (ps), crossover population, skill matrix, total number of skills required per workstation |
| 2 | output: The mutated solution |
| 3 | begin |
| 4 | while the mutant chromosome count < ps do |
| 5 | if rand () < pm then |
| 6 | Randomly pick a chromosome from the non-elite set |
| 7 | Repeat |
| 8 | Select two random positions, swap1 and swap2, ensuring swap2 > swap1 |
| 9 | Let the workstation at swap1 be denoted as x and that at swap2 as y |
| 10 | Until x and y have a common skill |
| 11 | Determine skills and worker demand for x and y |
| 12 | Determine overlapping skills for x and y |
| 13 | For every overlapping skill type do |
| 14 | Determine the workers linked to x and y for the given skill |
| 15 | Randomly pick one worker from x and another from y |
| 16 | if worker from x ∉ y and worker from y ∉ x then |
| 17 | Swap the positions of the selected workers between workstations x and y |
| 18 | end if |
| 19 | end for |
| 20 | end if |
| 21 | end while |
| 22 | Return the mutated population |
| 23 | end |

Appendix E. Metric definitions, equations, and calculation procedures

The comparison metrics employed in this study evaluate different characteristics of the obtained Pareto solution sets. The distance-based metrics, namely IGD, MID, SP, and SNS, are used to assess the convergence, distribution, and overall quality of the non-dominated solutions. Since these metrics provide complementary information, they constitute the primary basis for comparing the proposed workforce configurations. In addition, the number of Pareto solutions (NPS) is used to quantify the number of non-dominated solutions generated under each workforce configuration, while the coverage metric C(E,C) is employed to evaluate the dominance relationship between pairs of workforce configurations. By jointly analyzing these complementary metrics, a more comprehensive and reliable evaluation of the proposed workforce configurations is achieved. The detailed definitions of each metric are provided as follows.

Before introducing the individual metrics, it should be noted that total labor cost, makespan, and workload imbalance are measured on different numerical scales. Therefore, all objective values are normalized before calculating the distance-based metrics, namely IGD, MID, SP, and SNS. For each experimental instance, a common empirical reference set is constructed by combining the non-dominated solutions obtained under the four workforce configurations (A1–A4) and removing duplicate and dominated solutions. The minimum and maximum objective values of this common reference set are then used in EC (2), and the same normalization limits are applied to all four workforce configurations. Consequently, all distance calculations are performed in a common normalized objective space.

C(E,C) compares pareto solutions and it is calculated using EC (1). This metric evaluates the dominance relationship between two Pareto solution sets and is employed in this study to compare the workforce configurations (Gürsoy Yılmaz et al., 2024). Specifically, C(E,C) quantifies the proportion of solutions in set C that are outperformed by one or more solutions contained in set E. A higher value of C(E,C) implies that the non-dominated solutions in E demonstrate superior performance compared to those in C. Due to the asymmetry of this metric, C(E,C) must also be calculated separately, as CE,C≠1- CE,C.

f1*.=|{b∈C|∃a∈E:a≺b}||C|                                                                                                                                         (1)

One of the important metrics is the inverted generational distance (IGD). This metric assesses how well the obtained Pareto solutions approximate the true Pareto front. Moreover, IGD computes the average distance from each point in a reference set (typically representing the true Pareto front) to the nearest solution in the approximated Pareto front (Chen et al., 2015). The IGD metric is shown in EC (2) and (3).

IGDP,P*=1|P*|x∈P*mindis(x,P)                                                                                                                             (2)

mindisx,P=minx∈Pi=1p(fi*x-fi*y)2                                                                                                               (3)

fi*.=fi.-fmini(P*)fmaxiP*-fmini(P*)                                                                                                                                        (4)

where P* denotes the reference solution set (ideal Pareto front) and P represents the approximated Pareto solution set, mindisx,P refers to the minimum Euclidean distance between a point x∈P* and the closest point in P. The term |P*| corresponds to the number of points in the reference set. This formulation calculates the average minimum distance from the reference set to the approximation set, providing a measure of how closely the obtained Pareto solutions approximate the true Pareto front. Additionally, fi*. denotes the normalized value of the ith objective function, obtained using EC (4). Furthermore, smaller IGD values indicate higher-quality solutions, as they reflect closer proximity to the ideal Pareto front.

Continuing with the metrics, mean ideal distance (MID) metric quantifies the average distance of solutions from the ideal point in the objective space (Karimi et al., 2010). It is determined using EC (5).

MID=1Ni=1Nci                                                                                                                                                                         (5)

In addition, ci is computed using EC (6).

ci=(f1i*)2+(f2i*)2+(f3i*)2                                                                                                                                               (6)

Here, N denotes the number of non-dominated solutions, and f1i*, f2i* and f3i* denote the normalized values of the three objective functions for the ith non-dominated solution, obtained using EC (25). A smaller MID value indicates that the solutions are, on average, closer to the normalized ideal point, reflecting better convergence in multi-objective optimization.

On the other hand, a related metric to the MID is the spread of non-dominated solutions (SNS), which is used to evaluate the distribution of the obtained solutions. The SNS is calculated using EC (28).

SNS=1N-1i=1N(MID-ci)2                                                                                                                                           (7)

Since both MID and ci​ are computed using normalized objective values (EC (4)), SNS is also evaluated in the normalized objective space. Higher SNS values indicate greater dispersion of the non-dominated solutions around their mean distance from the ideal point (Karimi et al., 2010). Therefore, SNS should be interpreted together with convergence-oriented metrics such as IGD and MID.

The spacing metric (SP) proposed by Schott (1995) evaluates the uneven distribution of solutions by calculating the variance of distances between the solutions and the average distance. This provides a measure of how uniformly the solutions are distributed in the objective space. A smaller SP value, calculated using EC (8), indicates a more uniform distribution of non-dominated solutions along the Pareto front.

SP=1N-1i=1N(d-di)2                                                                                                                                                    (8)

where N denotes the number of non-dominated solutions, d represents the average distance between the solutions, and di is the distance of the ith solution to its nearest neighbor.

Finally, the number of pareto solutions (NPS) metric evaluates the size of the Pareto front by measuring the cardinality of the set of non-dominated solutions (Hajipour et al., 2016). This metric provides a quantitative measure of the number of distinct solutions in the Pareto front. A higher NPS value indicates a broader and more diverse solution set. NPS is determined using EC (9).

NPS=PF                                                                                                                                                                                (9)

Appendix F. Taguchi Results

Table F1. The metrics values for the fifth run of the A4 (NSGA-II-S4-MS)

| ps | pc | pm | ni | NPS | IGD | SP | MID | SNS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 50 | 0.7 | 0.05 | 250 | 50 | 0.1383 | 0.1247 | 0.5969 | 0.1278 |
| 50 | 0.8 | 0.1 | 500 | 50 | 0.1100 | 0.1643 | 0.7258 | 0.1768 |
| 50 | 0.9 | 0.15 | 750 | 50 | 0.1512 | 0.1846 | 0.7527 | 0.2601 |
| 100 | 0.7 | 0.1 | 750 | 72 | 0.0401 | 0.1608 | 0.5607 | 0.1606 |
| 100 | 0.8 | 0.15 | 250 | 69 | 0.1259 | 0.0966 | 0.7244 | 0.1201 |
| 100 | 0.9 | 0.05 | 500 | 49 | 0.0874 | 0.1641 | 0.7012 | 0.1536 |
| 150 | 0.7 | 0.15 | 500 | 76 | 0.1280 | 0.1151 | 0.6684 | 0.1433 |
| 150 | 0.8 | 0.05 | 750 | 62 | 0.0635 | 0.1249 | 0.7423 | 0.2122 |
| 150 | 0.9 | 0.1 | 250 | 67 | 0.0860 | 0.1087 | 0.5171 | 0.1489 |

Table F2. Normalized metrics values for the fifth run of the A4 (NSGA-II-S4-MS)

| ps | pc | pm | ni | NPS | IGD | SP | MID | SNS | Sum5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 50 | 0.7 | 0.05 | 250 | 0.6578 | 0.2899 | 0.7745 | 0.8663 | 0.4912 | 3.0798 |
| 50 | 0.8 | 0.1 | 500 | 0.6578 | 0.3645 | 0.5881 | 0.7124 | 0.6798 | 3.0029 |
| 50 | 0.9 | 0.15 | 750 | 0.6578 | 0.2652 | 0.5235 | 0.6869 | 1 | 3.1336 |
| 100 | 0.7 | 0.1 | 750 | 0.9473 | 1 | 0.6008 | 0.9222 | 0.6172 | 4.0877 |
| 100 | 0.8 | 0.15 | 250 | 0.9078 | 0.3184 | 1 | 0.7138 | 0.4616 | 3.4019 |
| 100 | 0.9 | 0.05 | 500 | 0.6447 | 0.4591 | 0.5889 | 0.7374 | 0.5905 | 3.0207 |
| 150 | 0.7 | 0.15 | 500 | 1 | 0.3132 | 0.8391 | 0.7736 | 0.5508 | 3.4769 |
| 150 | 0.8 | 0.05 | 750 | 0.8157 | 0.6312 | 0.7737 | 0.6965 | 0.8158 | 3.7332 |
| 150 | 0.9 | 0.1 | 250 | 0.8815 | 0.4663 | 0.8886 | 1 | 0.5725 | 3.8090 |

Table F3. Taguchi experimental results and S/N values for the all run of the A4 (NSGA-II-S4-MS)

| ps | pc | pm | ni | Sum1 | Sum2 | Sum3 | Sum4 | Sum5 | S/N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 50 | 0.7 | 0.05 | 250 | 2.7149 | 3.2063 | 2.5041 | 2.5092 | 3.0799 | 8.8162 |
| 50 | 0.8 | 0.1 | 500 | 2.4598 | 3.6852 | 3.0664 | 2.5920 | 3.0029 | 9.1722 |
| 50 | 0.9 | 0.15 | 750 | 2.5717 | 3.0626 | 3.4134 | 2.6715 | 3.1336 | 9.3137 |
| 100 | 0.7 | 0.1 | 750 | 3.1287 | 3.7533 | 3.6873 | 3.5163 | 4.0877 | 11.107 |
| 100 | 0.8 | 0.15 | 250 | 2.7217 | 3.5830 | 4.1855 | 2.9630 | 3.4020 | 10.266 |
| 100 | 0.9 | 0.05 | 500 | 3.4011 | 3.8106 | 3.4050 | 2.8139 | 3.0207 | 10.200 |
| 150 | 0.7 | 0.15 | 500 | 3.3371 | 3.5057 | 3.8003 | 3.2090 | 3.4770 | 10.754 |
| 150 | 0.8 | 0.05 | 750 | 3.6100 | 3.8340 | 3.9374 | 3.4057 | 3.7332 | 11.340 |
| 150 | 0.9 | 0.1 | 250 | 3.7152 | 3.0804 | 3.0541 | 4.0652 | 3.8091 | 10.814 |

Appendix G. CPU times for A1-A4

Figure G1. Average CPU times of the four workforce configurations (A1–A4) across different ∣L∣ levels.

Appendix H

Table H1. IGD, MID, SP and SNS values of the proposed workforce configurations with respect to all |L| values

| IGD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | ¦ L ¦=5 |  |  |  |  |  |  | ¦ L ¦=7 |  |  |  |  |  |  |  |  |  | ¦ L ¦=9 |  |  |  |  |  |  |  |  |  |  |  |  |
| ¦I¦ | ¦S¦ |  | ¦W¦ |  | A1 | A2 |  | A3 |  | A4 |  | A1 | A2 |  |  | A3 |  |  | A4 |  |  | A1 |  |  | A2 |  |  |  | A3 |  |  |  | A4 |  |
| 12 | 5 |  | 30 |  | 0.8757 | 0.0646 |  | 0.3646 |  | 0.0820 |  | 0.9145 | 0.1537 |  |  | 0.4381 |  |  | 0.1248 |  |  | 1.0933 |  |  | 0.2791 |  |  |  | 0,5701 |  |  |  | 0,1678 |  |
| 12 | 5 |  | 40 |  | 0.9110 | 0.0956 |  | 0.4254 |  | 0.1940 |  | 0.9267 | 0.0800 |  |  | 0.4154 |  |  | 0.1296 |  |  | 0.9625 |  |  | 0.1150 |  |  |  | 0,4644 |  |  |  | 0,1417 |  |
| 12 | 5 |  | 50 |  | 0.9700 | 0.0793 |  | 0.4998 |  | 0.1018 |  | 1.0311 | 0.0695 |  |  | 0.4310 |  |  | 0.1217 |  |  | 0.9790 |  |  | 0.0819 |  |  |  | 0,5368 |  |  |  | 0,1082 |  |
| 12 | 10 |  | 30 |  | 0.9057 | 0.1647 |  | 0.3306 |  | 0.0503 |  | 1.0126 | 0.2530 |  |  | 0.5535 |  |  | 0.1016 |  |  | 0.9727 |  |  | 0.2555 |  |  |  | 0,4399 |  |  |  | 0,1306 |  |
| 12 | 10 |  | 40 |  | 0.8890 | 0.1093 |  | 0.3456 |  | 0.1318 |  | 1.0819 | 0.1087 |  |  | 0.4324 |  |  | 0.1004 |  |  | 0.9636 |  |  | 0.0911 |  |  |  | 0,3833 |  |  |  | 0,1050 |  |
| 12 | 10 |  | 50 |  | 0.9141 | 0.0740 |  | 0.3254 |  | 0.0329 |  | 1.0297 | 0.1625 |  |  | 0.4016 |  |  | 0.1222 |  |  | 0.9926 |  |  | 0.1244 |  |  |  | 0,4582 |  |  |  | 0,1586 |  |
| 12 | 15 |  | 30 |  | 0.9232 | 0.2774 |  | 0.3586 |  | 0.0838 |  | 0.9540 | 0.2896 |  |  | 0.3161 |  |  | 0.0607 |  |  | 0.9849 |  |  | 0.2029 |  |  |  | 0,3233 |  |  |  | 0,0908 |  |
| 12 | 15 |  | 40 |  | 0.8630 | 0.1283 |  | 0.3030 |  | 0.0363 |  | 0.9092 | 0.1803 |  |  | 0.3893 |  |  | 0.0506 |  |  | 1.0577 |  |  | 0.2005 |  |  |  | 0,4496 |  |  |  | 0,0846 |  |
| 12 | 15 |  | 50 |  | 0.9076 | 0.1154 |  | 0.3017 |  | 0.0514 |  | 0.8921 | 0.1190 |  |  | 0.3183 |  |  | 0.1034 |  |  | 0.9822 |  |  | 0.1418 |  |  |  | 0,3702 |  |  |  | 0,0727 |  |
| 16 | 5 |  | 30 |  | 0.9266 | 0.1091 |  | 0.4293 |  | 0.1130 |  | 0.8466 | 0.1388 |  |  | 0.4366 |  |  | 0.0947 |  |  | 0.9294 |  |  | 0.1120 |  |  |  | 0,4770 |  |  |  | 0,0986 |  |
| 16 | 5 |  | 40 |  | 0.9257 | 0.1101 |  | 0.3408 |  | 0.0994 |  | 0.9376 | 0.0970 |  |  | 0.4133 |  |  | 0.0894 |  |  | 0.9266 |  |  | 0.1439 |  |  |  | 0,4260 |  |  |  | 0,1010 |  |
| 16 | 5 |  | 50 |  | 0.9058 | 0.0725 |  | 0.4723 |  | 0.0972 |  | 0.9117 | 0.0463 |  |  | 0.4205 |  |  | 0.0613 |  |  | 0.8910 |  |  | 0.0490 |  |  |  | 0,4057 |  |  |  | 0,1262 |  |
| 16 | 10 |  | 30 |  | 0.8171 | 0.1255 |  | 0.3400 |  | 0.0938 |  | 0.9159 | 0.1233 |  |  | 0.3784 |  |  | 0.1052 |  |  | 0.9606 |  |  | 0.3678 |  |  |  | 0,3936 |  |  |  | 0,1790 |  |
| 16 | 10 |  | 40 |  | 0.9396 | 0.1649 |  | 0.3770 |  | 0.0616 |  | 0.9557 | 0.2054 |  |  | 0.3847 |  |  | 0.0542 |  |  | 0.9208 |  |  | 0.1173 |  |  |  | 0,3757 |  |  |  | 0,1003 |  |
| 16 | 10 |  | 50 |  | 0.9132 | 0.0659 |  | 0.3311 |  | 0.0726 |  | 1.0218 | 0.1039 |  |  | 0.4335 |  |  | 0.0626 |  |  | 0.9822 |  |  | 0.1596 |  |  |  | 0,4016 |  |  |  | 0,0928 |  |
| 16 | 15 |  | 30 |  | 0.9022 | 0.2272 |  | 0.4078 |  | 0.0405 |  | 1.3775 | 0.5071 |  |  | 0.5096 |  |  | 0.0456 |  |  | 0.9782 |  |  | 0.2769 |  |  |  | 0,4064 |  |  |  | 0,1124 |  |
| 16 | 15 |  | 40 |  | 0.8543 | 0.1820 |  | 0.3188 |  | 0.0884 |  | 0.8998 | 0.1546 |  |  | 0.3449 |  |  | 0.1191 |  |  | 0.9753 |  |  | 0.2157 |  |  |  | 0,4537 |  |  |  | 0,1261 |  |
| 16 | 15 |  | 50 |  | 0.9401 | 0.1790 |  | 0.3423 |  | 0.0441 |  | 0.9752 | 0.1052 |  |  | 0.4423 |  |  | 0.1463 |  |  | 0.8272 |  |  | 0.0763 |  |  |  | 0,3100 |  |  |  | 0,0760 |  |
| 20 | 5 |  | 30 |  | 0.9038 | 0.1066 |  | 0.3774 |  | 0.0797 |  | 0.9043 | 0.1047 |  |  | 0.4344 |  |  | 0.1388 |  |  | 1.0195 |  |  | 0.1000 |  |  |  | 0,5453 |  |  |  | 0,1454 |  |
| 20 | 5 |  | 40 |  | 0.9486 | 0.0686 |  | 0.4095 |  | 0.0899 |  | 0.8752 | 0.0732 |  |  | 0.3962 |  |  | 0.0896 |  |  | 0.9989 |  |  | 0.1035 |  |  |  | 0,4908 |  |  |  | 0,1241 |  |
| 20 | 5 |  | 50 |  | 0.9203 | 0.0656 |  | 0.4749 |  | 0.0535 |  | 0.8993 | 0.0863 |  |  | 0.3008 |  |  | 0.0735 |  |  | 0.9017 |  |  | 0.1066 |  |  |  | 0,3959 |  |  |  | 0,1097 |  |
| 20 | 10 |  | 30 |  | 0.8888 | 0.1078 |  | 0.4448 |  | 0.1122 |  | 0.9176 | 0.1081 |  |  | 0.3649 |  |  | 0.0452 |  |  | 0.8968 |  |  | 0.2631 |  |  |  | 0,3855 |  |  |  | 0,0663 |  |
| 20 | 10 |  | 40 |  | 0.8902 | 0.1313 |  | 0.3716 |  | 0.0794 |  | 0.9288 | 0.1100 |  |  | 0.4462 |  |  | 0.1423 |  |  | 0.8314 |  |  | 0.1575 |  |  |  | 0,3336 |  |  |  | 0,1398 |  |
| 20 | 10 |  | 50 |  | 0.9017 | 0.0851 |  | 0.3278 |  | 0.1072 |  | 0.9161 | 0.0785 |  |  | 0.3624 |  |  | 0.0794 |  |  | 0.9418 |  |  | 0.1400 |  |  |  | 0,3717 |  |  |  | 0,1016 |  |
| 20 | 15 |  | 30 |  | 1.1371 | 0.3529 |  | 0.6036 |  | 0.1299 |  | 0.9308 | 0.2660 |  |  | 0.4178 |  |  | 0.0425 |  |  | 0.9387 |  |  | 0.2851 |  |  |  | 0,3272 |  |  |  | 0,0492 |  |
| 20 | 15 |  | 40 |  | 0.8609 | 0.1776 |  | 0.3831 |  | 0.1166 |  | 0.8294 | 0.1395 |  |  | 0.2849 |  |  | 0.0612 |  |  | 0.8938 |  |  | 0.3052 |  |  |  | 0,3182 |  |  |  | 0,0499 |  |
| 20 | 15 |  | 50 |  | 0.8789 | 0.1496 |  | 0.3960 |  | 0.1337 |  | 0.8828 | 0.0979 |  |  | 0.3494 |  |  | 0.0886 |  |  | 0.9313 |  |  | 0.1696 |  |  |  | 0,3404 |  |  |  | 0,0858 |  |
| Average |  |  |  |  | 0.9116 | 0.1329 |  | 0.3853 |  | 0.0880 |  | 0.9510 | 0.1467 |  |  | 0.4006 |  |  | 0.0909 |  |  | 0.9531 |  |  | 0.1719 |  |  |  | 0.4131 |  |  |  | 0.1090 |  |
| MID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | ¦ L ¦=5 |  |  |  |  |  |  | ¦ L ¦=7 |  |  |  |  |  |  |  |  |  | ¦ L ¦=9 |  |  |  |  |  |  |  |  |  |  |  |  |
| ¦I¦ | ¦S¦ |  | ¦W¦ |  | A1 | A2 |  | A3 |  | A4 |  | A1 | A2 |  |  | A3 |  |  | A4 |  |  | A1 |  |  | A2 |  |  |  | A3 |  |  |  | A4 |  |
| 12 | 5 |  | 30 |  | 1.0672 | 0.6689 |  | 0.7651 |  | 0.7623 |  | 1.1647 | 0.7433 |  |  | 0.9381 |  |  | 0.6943 |  |  | 1.3637 |  |  | 0.8771 |  |  |  | 1,0358 |  |  |  | 0,6930 |  |
| 12 | 5 |  | 40 |  | 1.1088 | 0.7449 |  | 0.8300 |  | 0.6698 |  | 1.1389 | 0.6980 |  |  | 0.8477 |  |  | 0.6779 |  |  | 1.1685 |  |  | 0.7039 |  |  |  | 0,8855 |  |  |  | 0,7511 |  |
| 12 | 5 |  | 50 |  | 1.0579 | 0.6773 |  | 0.8443 |  | 0.7366 |  | 1.2870 | 0.7504 |  |  | 0.9512 |  |  | 0.8296 |  |  | 1.1203 |  |  | 0.6675 |  |  |  | 0,8831 |  |  |  | 0,6305 |  |
| 12 | 10 |  | 30 |  | 1.1376 | 0.7181 |  | 0.7199 |  | 0.6530 |  | 1.2900 | 0.8486 |  |  | 0.9690 |  |  | 0.6226 |  |  | 1.2281 |  |  | 0.8567 |  |  |  | 0,8823 |  |  |  | 0,7006 |  |
| 12 | 10 |  | 40 |  | 1.0664 | 0.7139 |  | 0.7784 |  | 0.6674 |  | 1.2726 | 0.6873 |  |  | 0.9186 |  |  | 0.7368 |  |  | 1.1409 |  |  | 0.7349 |  |  |  | 0,8596 |  |  |  | 0,7071 |  |
| 12 | 10 |  | 50 |  | 1.0241 | 0.6540 |  | 0.7718 |  | 0.6959 |  | 1.1836 | 0.7823 |  |  | 0.8083 |  |  | 0.8081 |  |  | 1.2336 |  |  | 0.7966 |  |  |  | 0,8766 |  |  |  | 0,7219 |  |
| 12 | 15 |  | 30 |  | 1.1128 | 0.8445 |  | 0.7743 |  | 0.7236 |  | 1.1578 | 0.8355 |  |  | 0.8236 |  |  | 0.6810 |  |  | 1.2358 |  |  | 0.8531 |  |  |  | 0,8888 |  |  |  | 0,7160 |  |
| 12 | 15 |  | 40 |  | 1.0337 | 0.8048 |  | 0.8201 |  | 0.7018 |  | 1.0736 | 0.7851 |  |  | 0.9663 |  |  | 0.7252 |  |  | 1.2920 |  |  | 0.7582 |  |  |  | 0,9600 |  |  |  | 0,6596 |  |
| 12 | 15 |  | 50 |  | 1.0258 | 0.6855 |  | 0.7674 |  | 0.7098 |  | 1.1046 | 0.7492 |  |  | 0.8111 |  |  | 0.7128 |  |  | 1.1714 |  |  | 0.8137 |  |  |  | 0,8619 |  |  |  | 0,7055 |  |
| 16 | 5 |  | 30 |  | 1.1309 | 0.7460 |  | 0.8497 |  | 0.6946 |  | 1.0986 | 0.7477 |  |  | 0.8473 |  |  | 0.6722 |  |  | 1.1333 |  |  | 0.6738 |  |  |  | 0,8449 |  |  |  | 0,6329 |  |
| 16 | 5 |  | 40 |  | 1.1422 | 0.7938 |  | 0.8143 |  | 0.7393 |  | 1.0477 | 0.7341 |  |  | 0.7183 |  |  | 0.5884 |  |  | 1.1315 |  |  | 0.7586 |  |  |  | 0,8013 |  |  |  | 0,6883 |  |
| 16 | 5 |  | 50 |  | 1.0503 | 0.6899 |  | 0.8438 |  | 0.6694 |  | 1.0290 | 0.6544 |  |  | 0.7115 |  |  | 0.6654 |  |  | 1.0554 |  |  | 0.6910 |  |  |  | 0,8201 |  |  |  | 0,6374 |  |
| 16 | 10 |  | 30 |  | 1.0877 | 0.7292 |  | 0.7650 |  | 0.6589 |  | 1.1403 | 0.7589 |  |  | 0.9664 |  |  | 0.6884 |  |  | 1.2848 |  |  | 0.9560 |  |  |  | 0,8983 |  |  |  | 0,6399 |  |
| 16 | 10 |  | 40 |  | 1.1065 | 0.7833 |  | 0.8179 |  | 0.6675 |  | 1.1484 | 0.7981 |  |  | 0.8850 |  |  | 0.6688 |  |  | 1.1290 |  |  | 0.7486 |  |  |  | 0,7764 |  |  |  | 0,6846 |  |
| 16 | 10 |  | 50 |  | 1.0534 | 0.6692 |  | 0.7003 |  | 0.6113 |  | 1.1685 | 0.7179 |  |  | 0.8192 |  |  | 0.7316 |  |  | 1.1408 |  |  | 0.7809 |  |  |  | 0,8415 |  |  |  | 0,6595 |  |
| 16 | 15 |  | 30 |  | 1.1436 | 0.9484 |  | 0.9509 |  | 0.6703 |  | 1.6889 | 1.2033 |  |  | 1.1518 |  |  | 0.6910 |  |  | 1.1572 |  |  | 0.9466 |  |  |  | 0,8447 |  |  |  | 0,7178 |  |
| 16 | 15 |  | 40 |  | 1.0695 | 0.7705 |  | 0.6851 |  | 0.5927 |  | 1.1648 | 0.8302 |  |  | 0.8736 |  |  | 0.7018 |  |  | 1.1986 |  |  | 0.7902 |  |  |  | 0,9161 |  |  |  | 0,7140 |  |
| 16 | 15 |  | 50 |  | 1.0549 | 0.7901 |  | 0.8101 |  | 0.7164 |  | 1.1588 | 0.8054 |  |  | 0.7938 |  |  | 0.7911 |  |  | 1.0664 |  |  | 0.6750 |  |  |  | 0,7465 |  |  |  | 0,5944 |  |
| 20 | 5 |  | 30 |  | 1.1220 | 0.6622 |  | 0.7732 |  | 0.5981 |  | 1.1567 | 0.6533 |  |  | 0.9411 |  |  | 0.6533 |  |  | 1.2521 |  |  | 0.5860 |  |  |  | 0,9053 |  |  |  | 0,7427 |  |
| 20 | 5 |  | 40 |  | 1.1145 | 0.7393 |  | 0.7983 |  | 0.6902 |  | 1.0706 | 0.6808 |  |  | 0.8409 |  |  | 0.6569 |  |  | 1.1807 |  |  | 0.7137 |  |  |  | 0,8768 |  |  |  | 0,7259 |  |
| 20 | 5 |  | 50 |  | 1.0407 | 0.6523 |  | 0.7873 |  | 0.6922 |  | 1.0492 | 0.7669 |  |  | 0.7644 |  |  | 0.7152 |  |  | 1.1166 |  |  | 0.7187 |  |  |  | 0,8619 |  |  |  | 0,6624 |  |
| 20 | 10 |  | 30 |  | 1.1273 | 0.6864 |  | 0.8782 |  | 0.6467 |  | 1.1499 | 0.6340 |  |  | 0.7983 |  |  | 0.6663 |  |  | 1.1008 |  |  | 0.8390 |  |  |  | 0,7436 |  |  |  | 0,6047 |  |
| 20 | 10 |  | 40 |  | 1.0595 | 0.7226 |  | 0.7866 |  | 0.6787 |  | 1.1412 | 0.5884 |  |  | 0.8847 |  |  | 0.6593 |  |  | 1.0922 |  |  | 0.7874 |  |  |  | 0,7435 |  |  |  | 0,5932 |  |
| 20 | 10 |  | 50 |  | 1.0705 | 0.6875 |  | 0.7436 |  | 0.6318 |  | 1.1028 | 0.7277 |  |  | 0.8449 |  |  | 0.6721 |  |  | 1.1250 |  |  | 0.8289 |  |  |  | 0,9271 |  |  |  | 0,6991 |  |
| 20 | 15 |  | 30 |  | 1.4340 | 0.9759 |  | 1.1087 |  | 0.7426 |  | 1.1141 | 0.8737 |  |  | 0.8762 |  |  | 0.7009 |  |  | 1.1315 |  |  | 0.7755 |  |  |  | 0,7552 |  |  |  | 0,6856 |  |
| 20 | 15 |  | 40 |  | 1.1094 | 0.8721 |  | 0.9663 |  | 0.6915 |  | 1.0555 | 0.7279 |  |  | 0.7466 |  |  | 0.5894 |  |  | 1.0671 |  |  | 0.7849 |  |  |  | 0,6818 |  |  |  | 0,6844 |  |
| 20 | 15 |  | 50 |  | 1.1483 | 0.7998 |  | 0.9154 |  | 0.6837 |  | 1.0653 | 0.6340 |  |  | 0.8159 |  |  | 0.6466 |  |  | 1.1131 |  |  | 0.8096 |  |  |  | 0,8003 |  |  |  | 0,7067 |  |
| Average |  |  |  |  | 1,1000 | 0,7493 |  | 0.8173 |  | 0.6813 |  | 1.1564 | 0.7562 |  |  | 0.8635 |  |  | 0.6906 |  |  | 1.1641 |  |  | 0.7750 |  |  |  | 0.8489 |  |  |  | 0.6799 |  |
| SP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | ¦ L ¦=5 |  |  |  |  |  |  | ¦ L ¦=7 |  |  |  |  |  |  |  |  |  | ¦ L ¦=9 |  |  |  |  |  |  |  |  |  |  |  |  |
| ¦I¦ | ¦S¦ |  | ¦W¦ |  | A1 | A2 |  | A3 |  | A4 |  | A1 | A2 |  |  | A3 |  |  | A4 |  |  | A1 |  | A2 |  |  |  | A3 |  |  |  | A4 |  |  |
| 12 | 5 |  | 30 |  | 0.0000 | 0.1344 |  | 0.0478 |  | 0.1199 |  | 0.0000 | 0.1072 |  |  | 0.0813 |  |  | 0.1141 |  |  | 0.0000 |  | 0.1328 |  |  |  | 0,0706 |  |  |  | 0,0922 |  |  |
| 12 | 5 |  | 40 |  | 0.0071 | 0.1383 |  | 0.0448 |  | 0.0843 |  | 0.0000 | 0.1223 |  |  | 0.0558 |  |  | 0.1134 |  |  | 0.0000 |  | 0.1263 |  |  |  | 0,0386 |  |  |  | 0,0959 |  |  |
| 12 | 5 |  | 50 |  | 0.0000 | 0.1182 |  | 0.0446 |  | 0.1124 |  | 0.0108 | 0.0948 |  |  | 0.0392 |  |  | 0.1704 |  |  | 0.0048 |  | 0.1005 |  |  |  | 0,0459 |  |  |  | 0,0766 |  |  |
| 12 | 10 |  | 30 |  | 0.0000 | 0.1436 |  | 0.0570 |  | 0.1084 |  | 0.0000 | 0.1333 |  |  | 0.0939 |  |  | 0.1084 |  |  | 0.0000 |  | 0.0915 |  |  |  | 0,0480 |  |  |  | 0,1285 |  |  |
| 12 | 10 |  | 40 |  | 0.0000 | 0.1157 |  | 0.0462 |  | 0.1009 |  | 0.0042 | 0.1007 |  |  | 0.0503 |  |  | 0.1331 |  |  | 0.0000 |  | 0.1349 |  |  |  | 0,0787 |  |  |  | 0,1325 |  |  |
| 12 | 10 |  | 50 |  | 0.0006 | 0.1417 |  | 0.0558 |  | 0.1206 |  | 0.0089 | 0.1000 |  |  | 0.0408 |  |  | 0.1374 |  |  | 0.0000 |  | 0.0991 |  |  |  | 0,0413 |  |  |  | 0,1084 |  |  |
| 12 | 15 |  | 30 |  | 0.0000 | 0.1125 |  | 0.0835 |  | 0.1207 |  | 0.0000 | 0.0908 |  |  | 0.0777 |  |  | 0.1522 |  |  | 0.0000 |  | 0.1005 |  |  |  | 0,1087 |  |  |  | 0,1498 |  |  |
| 12 | 15 |  | 40 |  | 0.0019 | 0.1196 |  | 0.0766 |  | 0.1128 |  | 0.0000 | 0.0970 |  |  | 0.0784 |  |  | 0.1243 |  |  | 0.0000 |  | 0.1154 |  |  |  | 0,0789 |  |  |  | 0,1179 |  |  |
| 12 | 15 |  | 50 |  | 0.0000 | 0.1051 |  | 0.0406 |  | 0.1300 |  | 0.0014 | 0.0870 |  |  | 0.0657 |  |  | 0.1393 |  |  | 0.0018 |  | 0.1365 |  |  |  | 0,0786 |  |  |  | 0,1142 |  |  |
| 16 | 5 |  | 30 |  | 0.0000 | 0.1235 |  | 0.0691 |  | 0.1391 |  | 0.0026 | 0.1189 |  |  | 0.0489 |  |  | 0.1120 |  |  | 0.0000 |  | 0.1128 |  |  |  | 0,0616 |  |  |  | 0,1175 |  |  |
| 16 | 5 |  | 40 |  | 0.0000 | 0.1357 |  | 0.0822 |  | 0.1213 |  | 0.0000 | 0.1103 |  |  | 0.0327 |  |  | 0.1098 |  |  | 0.0113 |  | 0.0982 |  |  |  | 0,0317 |  |  |  | 0,1171 |  |  |
| 16 | 5 |  | 50 |  | 0.0000 | 0.1253 |  | 0.0251 |  | 0.1141 |  | 0.0000 | 0.1142 |  |  | 0.0378 |  |  | 0.1040 |  |  | 0.0000 |  | 0.1074 |  |  |  | 0,0567 |  |  |  | 0,0747 |  |  |
| 16 | 10 |  | 30 |  | 0.0000 | 0.1057 |  | 0.0709 |  | 0.1123 |  | 0.0000 | 0.1210 |  |  | 0.0850 |  |  | 0.1372 |  |  | 0.0000 |  | 0.1471 |  |  |  | 0,0932 |  |  |  | 0,1328 |  |  |
| 16 | 10 |  | 40 |  | 0.0000 | 0.1370 |  | 0.0585 |  | 0.1273 |  | 0.0000 | 0.1409 |  |  | 0.1055 |  |  | 0.1365 |  |  | 0.0008 |  | 0.1175 |  |  |  | 0,0654 |  |  |  | 0,1199 |  |  |
| 16 | 10 |  | 50 |  | 0.0000 | 0.1223 |  | 0.0449 |  | 0.0954 |  | 0.0041 | 0.1159 |  |  | 0.0597 |  |  | 0.1127 |  |  | 0.0000 |  | 0.1408 |  |  |  | 0,0574 |  |  |  | 0,0908 |  |  |
| 16 | 15 |  | 30 |  | 0.0000 | 0.2955 |  | 0.1259 |  | 0.1340 |  | 0.0000 | 0.2047 |  |  | 0.1790 |  |  | 0.1182 |  |  | 0.0000 |  | 0.1333 |  |  |  | 0,0625 |  |  |  | 0,1151 |  |  |
| 16 | 15 |  | 40 |  | 0.0000 | 0.0879 |  | 0.0860 |  | 0.1023 |  | 0.0000 | 0.1671 |  |  | 0.0899 |  |  | 0.1119 |  |  | 0.0000 |  | 0.1101 |  |  |  | 0,0530 |  |  |  | 0,1464 |  |  |
| 16 | 15 |  | 50 |  | 0.0000 | 0.1448 |  | 0.0574 |  | 0.1115 |  | 0.0000 | 0.1574 |  |  | 0.0256 |  |  | 0.1106 |  |  | 0.0000 |  | 0.1097 |  |  |  | 0,0533 |  |  |  | 0,0846 |  |  |
| 20 | 5 |  | 30 |  | 0.0000 | 0.1816 |  | 0.0301 |  | 0.1105 |  | 0.0000 | 0.0857 |  |  | 0.0502 |  |  | 0.1242 |  |  | 0.0000 |  | 0.1073 |  |  |  | 0,0417 |  |  |  | 0,1992 |  |  |
| 20 | 5 |  | 40 |  | 0.0015 | 0.1144 |  | 0.0352 |  | 0.1656 |  | 0.0000 | 0.1159 |  |  | 0.0446 |  |  | 0.1149 |  |  | 0.0000 |  | 0.0972 |  |  |  | 0,0540 |  |  |  | 0,1388 |  |  |
| 20 | 5 |  | 50 |  | 0.0021 | 0.1078 |  | 0.0221 |  | 0.1406 |  | 0.0000 | 0.1090 |  |  | 0.0358 |  |  | 0.1246 |  |  | 0.0003 |  | 0.0942 |  |  |  | 0,0330 |  |  |  | 0,1251 |  |  |
| 20 | 10 |  | 30 |  | 0.0000 | 0.1529 |  | 0.0634 |  | 0.1155 |  | 0.0000 | 0.1390 |  |  | 0.0676 |  |  | 0.1248 |  |  | 0.0038 |  | 0.1464 |  |  |  | 0,0411 |  |  |  | 0,1030 |  |  |
| 20 | 10 |  | 40 |  | 0.0000 | 0.1593 |  | 0.0670 |  | 0.1070 |  | 0.0000 | 0.1177 |  |  | 0.0594 |  |  | 0.1325 |  |  | 0.0000 |  | 0.1150 |  |  |  | 0,0606 |  |  |  | 0,0989 |  |  |
| 20 | 10 |  | 50 |  | 0.0048 | 0.1063 |  | 0.0710 |  | 0.1075 |  | 0.0000 | 0.1069 |  |  | 0.0659 |  |  | 0.0928 |  |  | 0.0000 |  | 0.1153 |  |  |  | 0,0768 |  |  |  | 0,1119 |  |  |
| 20 | 15 |  | 30 |  | 0.0000 | 0.1868 |  | 0.1313 |  | 0.1170 |  | 0.0000 | 0.1532 |  |  | 0.0871 |  |  | 0.1349 |  |  | 0.0000 |  | 0.0825 |  |  |  | 0,0934 |  |  |  | 0,1282 |  |  |
| 20 | 15 |  | 40 |  | 0.0000 | 0.1738 |  | 0.1098 |  | 0.0944 |  | 0.0000 | 0.1412 |  |  | 0.0814 |  |  | 0.1210 |  |  | 0.0000 |  | 0.1201 |  |  |  | 0,0559 |  |  |  | 0,1076 |  |  |
| 20 | 15 |  | 50 |  | 0.0076 | 0.1213 |  | 0.0851 |  | 0.1307 |  | 0.0000 | 0.0930 |  |  | 0.0667 |  |  | 0.0895 |  |  | 0.0000 |  | 0.1161 |  |  |  | 0,0610 |  |  |  | 0,0854 |  |  |
| Average |  |  |  |  | 0.0010 | 0.1374 |  | 0.0641 |  | 0.1169 |  | 0.0012 | 0.1202 |  |  | 0.0669 |  |  | 0.1224 |  |  | 0.0008 |  | 0.1151 |  |  |  | 0.0608 |  |  |  | 0.1153 |  |  |
| SNS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | ¦ L ¦=5 |  |  |  |  |  |  | ¦ L ¦=7 |  |  |  |  |  |  |  |  |  | ¦ L ¦=9 |  |  |  |  |  |  |  |  |  |  |  |  |
| ¦I¦ | ¦S¦ |  | ¦W¦ |  | A1 | A2 |  | A3 |  | A4 |  | A1 | A2 |  | A3 |  |  | A4 |  |  | A1 |  | A2 |  |  |  | A3 |  |  |  | A4 |  |  |  |
| 12 | 5 |  | 30 |  | 0,0018 | 0,1650 |  | 0,0459 |  | 0,1775 |  | 0,0010 | 0,1711 |  | 0,0967 |  |  | 0,1667 |  |  | 0,0000 |  | 0,1587 |  |  |  | 0,0778 |  |  |  | 0,1464 |  |  |  |
| 12 | 5 |  | 40 |  | 0,0104 | 0,2271 |  | 0,0859 |  | 0,1204 |  | 0,0051 | 0,1859 |  | 0,0734 |  |  | 0,1628 |  |  | 0,0034 |  | 0,1758 |  |  |  | 0,0548 |  |  |  | 0,1421 |  |  |  |
| 12 | 5 |  | 50 |  | 0,0059 | 0,1740 |  | 0,0557 |  | 0,1665 |  | 0,0203 | 0,1601 |  | 0,0643 |  |  | 0,2672 |  |  | 0,0082 |  | 0,1586 |  |  |  | 0,0613 |  |  |  | 0,1099 |  |  |  |
| 12 | 10 |  | 30 |  | 0,0000 | 0,1716 |  | 0,0645 |  | 0,1763 |  | 0,0125 | 0,2096 |  | 0,1372 |  |  | 0,1582 |  |  | 0,0070 |  | 0,1374 |  |  |  | 0,0827 |  |  |  | 0,1864 |  |  |  |
| 12 | 10 |  | 40 |  | 0,0009 | 0,1578 |  | 0,0563 |  | 0,1496 |  | 0,0015 | 0,1488 |  | 0,0769 |  |  | 0,1764 |  |  | 0,0036 |  | 0,2069 |  |  |  | 0,1310 |  |  |  | 0,1797 |  |  |  |
| 12 | 10 |  | 50 |  | 0,0006 | 0,1732 |  | 0,0513 |  | 0,1869 |  | 0,0274 | 0,1980 |  | 0,0677 |  |  | 0,2002 |  |  | 0,0031 |  | 0,1740 |  |  |  | 0,0336 |  |  |  | 0,1478 |  |  |  |
| 12 | 15 |  | 30 |  | 0,0000 | 0,1552 |  | 0,0873 |  | 0,2418 |  | 0,0000 | 0,1312 |  | 0,1343 |  |  | 0,1793 |  |  | 0,0015 |  | 0,1454 |  |  |  | 0,1487 |  |  |  | 0,1762 |  |  |  |
| 12 | 15 |  | 40 |  | 0,0011 | 0,2221 |  | 0,1127 |  | 0,1741 |  | 0,0000 | 0,1549 |  | 0,1873 |  |  | 0,1786 |  |  | 0,0000 |  | 0,1719 |  |  |  | 0,1291 |  |  |  | 0,1490 |  |  |  |
| 12 | 15 |  | 50 |  | 0,0002 | 0,1455 |  | 0,0643 |  | 0,1839 |  | 0,0094 | 0,1642 |  | 0,1051 |  |  | 0,2028 |  |  | 0,0060 |  | 0,2229 |  |  |  | 0,0982 |  |  |  | 0,1402 |  |  |  |
| 16 | 5 |  | 30 |  | 0,0029 | 0,2114 |  | 0,0951 |  | 0,1847 |  | 0,0045 | 0,1711 |  | 0,0903 |  |  | 0,1565 |  |  | 0,0112 |  | 0,1548 |  |  |  | 0,0747 |  |  |  | 0,1669 |  |  |  |
| 16 | 5 |  | 40 |  | 0,0000 | 0,1929 |  | 0,0909 |  | 0,1864 |  | 0,0000 | 0,2010 |  | 0,0567 |  |  | 0,1531 |  |  | 0,0158 |  | 0,1754 |  |  |  | 0,0819 |  |  |  | 0,1579 |  |  |  |
| 16 | 5 |  | 50 |  | 0,0019 | 0,1733 |  | 0,0468 |  | 0,1363 |  | 0,0027 | 0,1795 |  | 0,0648 |  |  | 0,1621 |  |  | 0,0037 |  | 0,1705 |  |  |  | 0,0860 |  |  |  | 0,1010 |  |  |  |
| 16 | 10 |  | 30 |  | 0,0022 | 0,1514 |  | 0,0842 |  | 0,1609 |  | 0,0000 | 0,1707 |  | 0,1254 |  |  | 0,1752 |  |  | 0,0057 |  | 0,1979 |  |  |  | 0,1256 |  |  |  | 0,1821 |  |  |  |
| 16 | 10 |  | 40 |  | 0,0008 | 0,1879 |  | 0,0892 |  | 0,1643 |  | 0,0082 | 0,2098 |  | 0,1447 |  |  | 0,1719 |  |  | 0,0015 |  | 0,1972 |  |  |  | 0,0749 |  |  |  | 0,1488 |  |  |  |
| 16 | 10 |  | 50 |  | 0,0064 | 0,1748 |  | 0,0437 |  | 0,1305 |  | 0,0130 | 0,1669 |  | 0,0550 |  |  | 0,1448 |  |  | 0,0017 |  | 0,2391 |  |  |  | 0,0787 |  |  |  | 0,1302 |  |  |  |
| 16 | 15 |  | 30 |  | 0,0000 | 0,4583 |  | 0,1671 |  | 0,2058 |  | 0,0000 | 0,3391 |  | 0,2838 |  |  | 0,1657 |  |  | 0,0000 |  | 0,2089 |  |  |  | 0,0858 |  |  |  | 0,1957 |  |  |  |
| 16 | 15 |  | 40 |  | 0,0000 | 0,1733 |  | 0,1268 |  | 0,1412 |  | 0,0000 | 0,2462 |  | 0,1385 |  |  | 0,1668 |  |  | 0,0051 |  | 0,1492 |  |  |  | 0,0817 |  |  |  | 0,1974 |  |  |  |
| 16 | 15 |  | 50 |  | 0,0004 | 0,2010 |  | 0,0944 |  | 0,1690 |  | 0,0046 | 0,2464 |  | 0,0463 |  |  | 0,1468 |  |  | 0,0011 |  | 0,1808 |  |  |  | 0,0626 |  |  |  | 0,1087 |  |  |  |
| 20 | 5 |  | 30 |  | 0,0007 | 0,2315 |  | 0,1032 |  | 0,1423 |  | 0,0125 | 0,1340 |  | 0,1314 |  |  | 0,1749 |  |  | 0,0012 |  | 0,1332 |  |  |  | 0,0702 |  |  |  | 0,3016 |  |  |  |
| 20 | 5 |  | 40 |  | 0,0033 | 0,1960 |  | 0,0538 |  | 0,1735 |  | 0,0006 | 0,1579 |  | 0,0810 |  |  | 0,1342 |  |  | 0,0214 |  | 0,1432 |  |  |  | 0,1039 |  |  |  | 0,1973 |  |  |  |
| 20 | 5 |  | 50 |  | 0,0034 | 0,1520 |  | 0,0446 |  | 0,1966 |  | 0,0001 | 0,1767 |  | 0,0359 |  |  | 0,1689 |  |  | 0,0012 |  | 0,1554 |  |  |  | 0,0772 |  |  |  | 0,1582 |  |  |  |
| 20 | 10 |  | 30 |  | 0,0000 | 0,2087 |  | 0,1013 |  | 0,1674 |  | 0,0115 | 0,1682 |  | 0,0747 |  |  | 0,1714 |  |  | 0,0006 |  | 0,1980 |  |  |  | 0,0497 |  |  |  | 0,1745 |  |  |  |
| 20 | 10 |  | 40 |  | 0,0000 | 0,2349 |  | 0,0934 |  | 0,1702 |  | 0,0027 | 0,1366 |  | 0,1057 |  |  | 0,1891 |  |  | 0,0144 |  | 0,1796 |  |  |  | 0,0749 |  |  |  | 0,1289 |  |  |  |
| 20 | 10 |  | 50 |  | 0,0146 | 0,1710 |  | 0,0796 |  | 0,1645 |  | 0,0048 | 0,1917 |  | 0,0824 |  |  | 0,1360 |  |  | 0,0007 |  | 0,2095 |  |  |  | 0,0866 |  |  |  | 0,1404 |  |  |  |
| 20 | 15 |  | 30 |  | 0,0000 | 0,2240 |  | 0,1740 |  | 0,2009 |  | 0,0000 | 0,2562 |  | 0,1411 |  |  | 0,1796 |  |  | 0,0000 |  | 0,1097 |  |  |  | 0,1447 |  |  |  | 0,2016 |  |  |  |
| 20 | 15 |  | 40 |  | 0,0390 | 0,2503 |  | 0,1583 |  | 0,1932 |  | 0,0029 | 0,2140 |  | 0,1119 |  |  | 0,1654 |  |  | 0,0008 |  | 0,2037 |  |  |  | 0,0893 |  |  |  | 0,1781 |  |  |  |
| 20 | 15 |  | 50 |  | 0,0066 | 0,2101 |  | 0,1059 |  | 0,2094 |  | 0,0079 | 0,1358 |  | 0,0922 |  |  | 0,1321 |  |  | 0,0045 |  | 0,1875 |  |  |  | 0,0887 |  |  |  | 0,1449 |  |  |  |
| Average |  |  |  |  | 0.0038 | 0.1998 |  | 0.0880 |  | 0.1731 |  | 0.0057 | 0.1861 |  | 0.1039 |  |  | 0.1699 |  |  | 0.0046 |  | 0.1757 |  |  |  | 0.0872 |  |  |  | 0.1627 |  |  |  |